| 1:1 Chromebook Blended Learning Integration Whole Group and Flipped Classroom Instruction |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Stages | Stage 1 | Stage2 | Stage3 | Stage4 | Stage 5 | Stage6 |
| Communication | Email Face to Face Administration team, campus partners, innovation partners | Face to Face Administration team, campus partners, innovation partners | Email Invitation Face to Face Teachers and support staff | Email Tele Callout Face to face Teachers | Face to Face Student& Parent | Face to Face Teachers |
| Where & How | Campus meeting facility (library, conference office) -Face to face -Teams | Campus meeting facility (library, conference office) -Face to face -Teams | Part1: Face to Face Part 2: Online | Face to face Chromebook training Whole group Content Small grouping | Online training at home, school or technology HUB | Campus meeting facility (library, classroom) -Face to face -Teams |
| Topic (Reason for PL) | Create 1:1 Chromebook pilot for blended learning | - Forecast new resources and materials needed 2-3 years ahead - Begin purchasing and planning for needs | Purpose of Blended Learning To establish the purpose of blended learning and establish the benefits and impact of blended learning platform learning platforms | Asynchronous Learning and Synchronous Learning | Digital Citizenship | Backwards planning |
| Leader/ Presenters | - Principal - Administration team - PTO Representative | - Principal - Administration team - PTO Representative - Campus partners (tech team representative) | Technology Instructional Specialist Campus Partners (Tech Team) | District Technology Instructional Specialist Campus Partners (Tech Team) Administration Team | District Technology Specialist | District Technology Instructional Specialist Campus Partners (Tech Team) Administration Team |
| Date Duration of Lesson | January-March | April-May | June 3-day PL | August -September 2-week PL series | September 3hr 3hrs Participation Certificate of completion to receive Chromebook device | October -3hr PL November-3hr PL January-3hr PL |
| Learning Goal/ Objective | Conduct comprehensive review of all current resources to align to blended learning priorities. |  | Part1: Teachers will understand the purpose of blended learning and develop effective whole group and flipped instructional practices to close achievement gap. Part2: The teacher will participate in digital citizenship course and demonstrated understanding with an evaluation. | Asynchronous Learning and Synchronous Learning- The teacher will demonstrate knowledge of Asynchronous and Synchronous Learning with the purpose of developing effective blended learning instructional core. | participate in digital citizenship course and demonstrated understanding with an evaluation. | The teacher create effective digital lessons following backwards planning |
| Activities | Identify key partners in the school to form systems that support 1:1 Chromebook integration Create Surveys Create Voting Systems |  | Part1: Building interactive lessons through Padlet, Peardeck, FlipGrid, Google Suite and Screencastify. Part 2: Digital Citizenship interactive asynchronous modules through Learning.com | Model and demonstrate content 5E lessons utilizing 2-3 interactive and collaborative platforms. Show and tell | Parent University (parents will learn and focus on engagement digital resources and strategies to assist child with asynchronous instruction. Inform parents of what students are learning in school to develop support skills | 5E Lesson planning utilizing 2 new interactive platforms |
| Essential Principals | Collaboration |  | - Active Practice - Coaching - Continuous Specialist Modeling - Peer to peer coaching | - Active Practice - Coaching - Modeling - Small group Collaboration | - Active Practice - Modeling - Collaboration | - Active learning - Small group peer collaboration - Technology instructional specialist modeling |
| Resources | - Microsoft Teams, Google Suite - Stakeholder Surveys | - Microsoft Teams, Google Suite Chromebook terms and conditions | Microsoft Teams, Padlet, PearDeck Flip grid, Jam board, Screencastify, Google Suite Survey feedback teachers interests and needs forms | Chromebooks Microsoft Teams, Padlet, PearDeck Flip grid, Jam board, Screencastify, Google Suite Survey feedback teachers interests and needs forms | Chromebooks Learning.com Instructional Technology Specialist | Teams Support channel to ask Questions, instructional tech support, device tech support Peer Coaching Mentor Feedback How to guides/Short Videos Digital Instructional playlist |
| Collaboration Method | Collaboration and surveys |  | Technology Specialist lead small groups in breakout rooms Content and grade level grouping Peer Coaching during small groups Mentor feedback | Instructional Technology Specialist Content and grade level grouping Peer Coaching during small groups Check point feedback | Instructional Technology Specialist Peer Coaching during small groups Survey forms and feedback: interest and needs feedback Teams support channel | PLC Content small grouping Peer collaboration Peer coaching |